## Project Tracking
Business Technologies Project Tracker
| Projects | [6 empty] | Deliverable(s)
Status | Priority | Est. Start Date | Est. Deadline | Est. Days | Task | Assignee | Description | Deliverable | Actual Start Date | Actual End Date | Actual Number of Days
Operations Scorecard
COMPLETE |  | 2016-08-15 | 2016-08-25 | 10 | Custom Scorecard | Albert Martires |  |  | 2016-08-15 | 2016-08-26 | 11
COMPLETE |  | 2016-08-26 | 2016-08-31 | 5 | Adhoc Report | Albert Martires |  |  | 2016-08-26 | 2016-09-02 | 7
COMPLETE |  | 2016-08-15 | 2016-08-19 | 4 | Web Server (Dev) Troubleshooting | Albert Martires |  |  | 2016-08-15 | 2016-08-19 | 4
IN PROGRESS |  | 2016-09-01 | 2016-10-03 | 32 | Move front-end/back end to MOD | Albert Martires |  | MOD web server set up and BUSO approval | 2016-09-05 |  | 0
AWAITING |  | 2016-10-04 | 2016-10-17 | 13 | UAT | Albert Martires |  | UAT sign off
AWAITING |  | 2016-10-18 | 2016-11-11 | 24 | Move front-end/back end to PROD | Albert Martires |  | Application deployment
Project Plan
COMPLETE |  | 2016-08-22 | 2016-08-24 | 2 | Execute script on MOD server | Albert Martires |  |  | 2016-08-22 | 2016-08-24 | 2
COMPLETE |  | 2016-08-25 | 2016-08-29 | 4 | User Acceptance Testing | Albert Martires |  |  | 2016-08-24 | 2016-08-29 | 5
COMPLETE |  | 2016-08-29 | 2016-09-01 | 3 | Execute script on PROD server | Albert Martires |  |  | 2016-08-29 | 2016-09-01 | 3
Benefits Estimate
COMPLETE |  | 2016-09-07 | 2016-09-08 | 1 | Update benefit option on the table | Albert Martires |  |  | 2016-09-07 | 2016-09-07 | 0
COMPLETE |  | 2016-09-07 | 2016-09-08 | 1 | Update letter template | Albert Martires |  |  | 2016-09-07 | 2016-09-07 | 0
COMPLETE |  | 2016-09-08 | 2016-09-09 | 1 | Manual input of lump sum | Albert Martires |  |  | 2016-09-07 | 2016-09-08 | 1
IN PROGRESS |  | 2016-09-12 | 2016-09-26 | 14 | User Acceptance Testing | Albert Martires |  | UAT sign off | 2016-09-08 |  | 0
AWAITING |  | 2016-09-26 | 2016-09-29 | 3 | Move changes from MOD to PROD | Albert Martires |  | Application deployment |  |  | 0
SPRNT Tax DB
COMPLETE |  | 2016-08-09 | 2016-08-16 | 7 | Execute script on MOD server | Joyce Bermoy |  |  | 2016-08-16 | 2016-08-16 | 0
COMPLETE |  | 2016-08-24 | 2016-08-25 | 1 | Load changes in data to production | Joyce Bermoy |  |  | 2016-08-25 | 2016-08-25 | 0
COMPLETE |  | 2016-08-17 | 2016-09-01 | 15 | User Acceptance Testing | Joyce Bermoy |  |  | 2016-08-17 | 2016-09-01 | 15
COMPLETE |  | 2016-09-06 | 2016-09-16 | 10 | Move changes from MOD to PROD | Joyce Bermoy |  |  | 2016-09-06 | 2016-09-12 | 6
Sprnt Tax Team Balancing
COMPLETE |  | 2016-05-27 | 2016-09-02 | 98 | Review Discrepancies | Joyce Bermoy |  |  | 2016-05-27 | 2016-09-02 | 98
COMPLETE |  | 2016-08-24 | 2016-08-26 | 2 | Update the query to not include the tax type of NYC in calculating total for State | Joyce Bermoy |  |  | 2016-08-24 | 2016-08-25 | 1
COMPLETE |  | 2016-08-24 | 2016-08-26 | 2 | Move changes from MOD to PROD | Joyce Bermoy |  |  | 2016-08-24 | 2016-08-25 | 1
Structured Settlement
IN PROGRESS |  | 2016-08-12 | 2016-10-14 | 63 | Automate Jobs for Payee Report | Joyce Bermoy |  |  | 2016-08-15 |  | 0
COMPLETE |  | 2016-08-23 | 2016-08-30 | 7 | Batch Update of Court Order, Offset and Core Data items | Joyce Bermoy |  |  | 2016-08-23 | 2016-08-31 | 8
DoNotCall
COMPLETE |  | 2016-09-02 | 2016-09-09 | 7 | Deployment in Prod | Nick Sarmiento |  | REM and SNOW CHG | 2016-09-02 | 2016-09-09 | 7
TIN Matching V2
IN PROGRESS |  | 2016-08-30 | 2016-09-30 | 31 | UAT | Nick Sarmiento |  | UAT sign off | 2016-08-30 |  | 0
AWAITING |  | 2016-10-03 | 2016-10-14 | 11 | Move changes from MOD to PROD | Nick Sarmiento |  | Application deployment |  |  | 0
Formulas:
Est. Days = IF([Est. Start Date] = "",0,IF([Est. Deadline]="",0,DATEDIF([Est. Start Date],[Est. Deadline],"d")))
Actual Number of Days = IF([Actual Start Date]="",0,IF([Actual End Date]="",0,DATEDIF([Actual Start Date],[Actual End Date],"d")))
Note on D10: JH: From 09/09/2016 - change to 09/30/2016
Note on C33: JH: UAT Start Date
Note on D33: JH: From 09/30 change to 10/14
Note on C38: JH: UAT Start Date
Note on J38: JH: UAT Start Date

## Incident
Status | Priority | Est. Start Date | Est. Deadline | Est. Days | Task | Assignee | Description | Deliverable | Actual Start Date | Actual End Date | Actual Number of Days
SPRNT Tax DB
COMPLETE |  | 2016-09-13 | 2016-09-14 | 1 | Data type mismatch error | Joyce Bermoy |  |  | 2016-09-14 | 2016-09-14 | 0
AWAITING |  | 2016-09-19 | 2016-09-26 | 7 | Discrepancy on Run 5 Reports | Joyce Bermoy
Structured Settlement
IN PROGRESS |  | 2016-09-14 | 2016-09-23 | 9 | Needs to delete the denied core data | Joyce Bermoy |  |  | 2016-09-16 |  | 0
Formulas:
Est. Days = IF([Est. Start Date] = "",0,IF([Est. Deadline]="",0,DATEDIF([Est. Start Date],[Est. Deadline],"d")))
Actual Number of Days = IF([Actual Start Date]="",0,IF([Actual End Date]="",0,DATEDIF([Actual Start Date],[Actual End Date],"d")))